## Slide 1: General Specifications – public BID request for: Project: «Expansion of vehicle production capacity» Lot 11: - 2 Conveyor belts in the finition line

## Slide 2: SUMMARY
Purpose of the consultation
Planning / schedule

## Slide 3: Purpose of the consultation
Convoyer belts in the finition line
All handling and process equipment installed must be able to operate with the increased production capacity.
According to the technical specifications, each conveyor belt should have a length of 72000 mm and a width of 2900 mm. It must ensure that the vehicles it’s moving in automatically mode. The conveyor belts are in the assembly department.
The proposed process solutions must minimize the impact of civil engineering on the ground, without exceptions.
The purpose of the project is the delivery, installation and commissioning of a installation for:

## Slide 4: Planning / Schedule
Order S19 2019
Technical End of Study Agreement mechanics (ATFE) S24 2019
Reception an Customer Plant (RCP) S32 2019
Technical End of Procedure Agreement (ATFMR) S35 2019
Technical Reception Agreement (ATMP) S38 2019
Performance Obtaining Statement (COP) S08 2020